## SOPO Template
Project Title: |  | [Enter Project Title]
Budget Period: |  | Budget Period designation ( 1 , 2 or 3 ) - Required for multi-year projects
Task Number | Task or Subtask (if applicable) Title | Milestone Type (Milestone or Go/No-Go Decision Point) | Milestone Number (Go/No-Go Decision Point Number) | Milestone Description (Go/No-Go Decision Criteria) | Milestone Verification Process (What, How, Who, Where) | Anticipated Date (Months from Start of the Project) | Anticipated Quarter (Quarters from Start of the Project)
TASK 1 | Demonstrate current and next-gen SoA Ir loading by direct and spray coating
1.1 | Achieve 3 A/cm2 at 1.8V with 0.3 mgIr/cm2 via spraycoating | Milestone |  |  |  | 6 | 2
1.1.1 | Development of catalyst ink recipes with ECSA and catalyst layer conductivity | Task | 1.1.1 |  |  | 2 | 1
1.1.2 | Electrolyzer testing of CCMs | Task | 1.1.2 |  |  | 4 | 2
1.1.3 | Optimization of catalyst layer deposition | Task | 1.1.3 |  |  | 6 | 2
1.2 | Demonstrate >3 A/cm2 at 1.8V with 0.4 mgIr/cm2 via direct coat | Milestone
1.2.1 | Slot-die coating uniformity optimization | Task | 1.2.1 |  |  | 2 | 1
1.2.2 | Development of catalyst ink depositions | Task | 1.2.2 |  |  | 4 | 2
1.2.3 | Optimization of catalyst layer deposition and sample delivery to Celadyne | Task | 1.2.3 |  |  | 6 | 2
1.2.4 | Electrolyzer testing of CCMs | Task | 1.2.4 |  |  | 6 | 2
|  | Go/No-Go Decision Point |  |  | Review meeting | 6 | 2
TASK 2 | Demonstrate R2R feasibility of DOE 2026 PGM target
2.1 | Achieve 3 A/cm2 at 1.8V with 0.4 mgPGM/cm2 via spraycoating | Milestone
2.1.1 | Electrolyzer testing of half CCMs | Task | 2.1.1 |  |  | 7 | 3
2.1.2 | Development of catalyst ink recipes with ECSA and catalyst layer conductivity | Task | 2.1.2 |  |  | 8 | 3
2.1.3 | Electrolyzer testing of CCMs | Task | 2.1.3 |  |  | 10 | 4
2.1.4 | Optimization of catalyst layer deposition | Task | 2.1.4 |  |  | 12 | 4
2.2 | Demonstrate >3 A/cm2 at 1.8V with 0.4 mgIr/cm2 via R2R | Milestone
2.2.1 | R2R coating uniformity optimization | Task | 2.2.1
2.2.2 | Optimization of catalyst layer deposition and sample delivery to Celadyne | Task | 2.2.2
2.2.3 | Electrolyzer testing of CCMs | Task | 2.2.3
|  | Go/No-Go Decision Point |  |  | Review meeting | 12 | 4
TASK 3 | Demonstrate DOE 2026 PGM target via R2R and integration into 5kW electrolyzer
3.1 | Demonstrate 3 A/cm2 at 1.8V with 0.4 mgPGM/cm2 via R2R | Milestone
3.1.1 | Electrolyzer testing of half CCMs | Task | 3.1.1 |  |  | 13 | 5
3.1.2 | Development of catalyst ink recipes with ECSA and catalyst layer conductivity | Task | 3.1.2 |  |  | 14 | 5
3.1.3 | Electrolyzer testing of CCMs | Task | 3.1.3 |  |  | 16 | 6
3.1.4 | Optimization of catalyst layer deposition | Task | 3.1.4 |  |  | 18 | 6
3.2 | Demonstrate 5kW electrolyzer operating at 3 A/cm2 at 1.8V/cell with 0.4 mgPGM/cm2 | Milestone
3.2.1 | Stack hardware selection and procurement | Task | 3.2.1 |  |  | 12 | 4
3.2.2 | Stack hardware single cell | Task | 3.2.2 |  |  | 13 | 5
3.2.3 | 1kW electrolyzer | Task | 3.2.3 |  |  | 15 | 5
3.2.4 | 5kW electrolyzer delivery | Task | 3.2.4 |  |  | 18 | 6
|  | Go/No-Go Decision Point |  |  | Review meeting | 18 | 6